## CP Open (hidden)
SET Control Panel Open Action Item List
Action Item # | CP/ERB | Document | Req.# | Action/Decision | Actionee | Due Date | Status
2009-06-05 | CP
060509-1 |  | 72205 Rev. F | 125 | Keep the Crane Requirement as is Do Not Change (Change in EISs as applicable)
060509-2 |  | VTC EIS |  | Change Crane requirement is this document to reflect the CSET 0125 requirement | Wiedenmannott | 2009-06-05
060509-32 |  |  | CSET0111 | O.K. to add this requirement (it is just a move) | Wiedenmannott | 2009-06-05
060509-33 |  |  |  | Update Cradle to reflect 72205 S. Wilson version 4/27
060509-34 |  |  |  | Issue updated VTC and HSDAS Specs with changes incorporated (in the Benham Specs and send to K. Kachmar | Wiedenmannott | 2009-06-05
2009-06-11 | CP
061909-28 | CP | VTC EIS | 19.5 oxygen Levels | Search and replace 19.5 with 21% within the document for oxygen levels | SE&I | 2009-06-25 | A. Bower, we need to delete and work another change request
2009-09-04 | CP
|  |  |  | Refurb Rack whith FY09 funds | H. Speier
|  |  |  | Requrest Orion Phase Shift | S. Motil
2009-09-17 | CP | ERB #2009-007 VTA Design Recommendation
09172009-01 |  |  |  | Review additional 22k costs and ensure availability | F Elliott
09172009-02 |  |  |  | Add control gates in the schedule for cost creep | D. Ludwiczak
09172009-03 |  |  |  | Add risks in the system for all hardware expected back from KSC (SASSs and Carts, etc.) | D. Ludwiczak
2009-09-17 | CP | SET SEMP
09172009-04 |  |  |  | When focusing on the next SEMP Revision, ensure Tvac updates are incorporated first and completed in time for the cryoshroud PDR | Wiedenmannott/Ludwiczak
09172009-05 |  |  |  | Ensure all other SEMP Revisions are completed prior to the E3/Tvac concept review | Wiedenmannott/Ludwiczak

## Closed (hidden)
SET Closed Action Items
Action Item # | CP/ERB | Document | Req.# | Action/Decision | Actionee | Due Date | Status
6/5/2009 CP
060509-1 | CP | 72205 Rev. F | 125 | Keep the Crane Requirement as is Do Not Change (Change in EISs as applicable)
060509-3 | CP | VTCEIS/72205 | CSET 0120 | Change Mass to Weight | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-4 | CP |  | CSET 0005 | Change Mass to Weight | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-5 | CP |  | CSET 0008 | O.K. to change as proposed | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-6 | CP |  | CSET 0038 Leve as is DO NOT CHANGE | Leave as is DO NOT CHANGE | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-7 | CP |  | CSET0015 | Leave as is DO NOT CHANGE | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-8 | CP |  | CSET0002 | Change Mass to Weight Modify rationale to read: All equipmentto provide modal testing will be provided by the customer except for HSDAS. Change assumes to "include". | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-9 | CP |  | CSET0013 | Leave as is DO NOT CHANGE | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-10 | CP |  | CSET 0126 | Leave as is DO NOT CHANGE | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-11 | CP |  | CSET0018 | Leave as is DO NOT CHANGE | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-12 | CP |  | CSET0027 | Damian to set up a mtg. with Benham and include J. Free and S. Motil. Leave as is DO NOT CHANGE | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-13 | CP |  | CSET0028 | Leave as is DO NOT CHANGE Damian to work the Benham verification issue | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-14 | CP |  | CSET0031 | Leave as is DO NOT CHANGE | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-15 | CP |  | CSET0125 | Accept Change to requirement but not the rationale | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-16 | CP |  | CSET0037 | Delete This Requirement in 72205 and in VTC EIS | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-17 | CP | VTC EIS | CSET0007 | Delete This Requirement and move to Facility EIS | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-18 | CP | Facility EIS | CSET0007 | Add this Requirement | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-19 | CP |  | CSET0024 | Delete this Requiremetn in 72205 and in VTC EIS | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-20 | CP |  | CSET 0101 | Delete this requirement in VTC EIS | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-21 | CP | HSDAS EIS |  | Add this Requirement | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-22 | CP |  | CSET0106 | Delete this requirement in VTC EIS | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-23 | CP | Facility EIS |  | Add this Requirement | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-24 | CP |  | CSET0108 | O.K to change as propsed | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-25 | CP |  | CSET0046 | Leave as is DO NOT CHANGE | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-26 | CP |  | CSET0050 | Leave as is DO NOT CHANGE | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-27 | CP |  | CSET0054 | Leave as is DO NOT CHANGE | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-28 | CP |  | CSET0056 | Leave as is DO NOT CHANGE | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-29 | CP |  | CSET0104 | Keep Requirement (it was just a move) Delete the rationale (the rationale was proposed as new and was rejected) | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-30 | CP |  | CSET0066 | Leave as is DO NOT CHANGE | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-31 | CP |  | CSET0069 | Leave as is DO NOT CHANGE | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-35 | CP |  |  | Delete page 3 of power point chart that states minor changes from 72205. There should be no differences | Wiedenmannott | 2009-06-05 | Closed in origial Baseline document released
060509-36 | CP |  |  | Send updated documents to team to review | Kachmar | 2009-06-08 | Closed in origial Baseline document released
060509-37 | CP |  |  | Schedule CP Reconvene next Thursday afternoon 2:00pm | Kachmar | 2009-06-08 | Closed in origial Baseline document released
6/11/2009 CP
061109-1 | CP | 72205 Rev. F | CSET 026 | Keep the red rationale except add " the other 32 channels are used for monitoring only" in the rationale | Wiedenmannott |  | Closed in origial Baseline document released
061109-2 | CP |  | CSET 027 | Keep the red rationale except add: 1. " the other 32 channels are used for monitoring only" in the rationale 2. Change the 32 to say 10 of the control channels will be available to the test article. 3. Also add to rationale that the channells are considered Test Critical and there are no spare channels available. | Wiedenmannott |  | Closed in origial Baseline document released
061109-3 | CP |  | CSET 049 | accept | Wiedenmannott |  | Closed in origial Baseline document released
061109-4 | CP |  | CSET050 | O.K. Keep red rationale in red, spell out thermal couple, add "pentration" at the end. | Wiedenmannott |  | Closed in origial Baseline document released
061109-5 | CP |  | CSET051 | accept | Wiedenmannott |  | Closed in origial Baseline document released
061109-6 | CP |  | CSET052 | Change to 32 and accept red rationale | Wiedenmannott |  | Closed in origial Baseline document released
061109-7 | CP |  | CSET0053 | accept | Wiedenmannott |  | Closed in origial Baseline document released
061109-8 | CP |  | CSET0054 | accept | Wiedenmannott |  | Closed in origial Baseline document released
061109-9 | CP |  | CSET0055 | accept | Wiedenmannott |  | Closed in origial Baseline document released
061109-10 | CP |  | CSET0056 | Spell out thermal couples | Wiedenmannott |  | Closed in origial Baseline document released
061109-11 | CP | E3 and 72205 | CSET0097 | accept | Wiedenmannott |  | Closed in origial Baseline document released
061109-12 | CP | E3 and 72205 | CSET0096 | K.Shalkhauser to re-write to relect what we are actually doing for 70080. This will be a proposed change to 72205 and the VTC EIS | Shalkhouser/ Wiedenmannott |  | Closed in origial Baseline document released
061109-13 | CP |  | CSET0100 | accept | Wiedenmannott |  | Closed in origial Baseline document released
061109-14 | CP | T/V and 72205 | CSET0077 | accept | Wiedenmannott |  | Closed in origial Baseline document released
061109-15 | CP | T/V and 72205 | CSET0078 | accept | Wiedenmannott |  | Closed in origial Baseline document released
061109-16 | CP | T/V and 72205 | CSET0079 | Take out TBR in requirement. The rationale should read "This weight is driven by the limitation of the cart" . | Wiedenmannott |  | Closed in origial Baseline document released
061109-17 | CP | T/V and 72205 | CSET0080 | accept | Wiedenmannott |  | Closed in origial Baseline document released
061109-18 | CP | T/V and 72205 | CSET0081 | accept | Wiedenmannott |  | Closed in origial Baseline document released
061109-19 | CP | T/V and 72205 | CSET0082 | correct the spelling on requirement. Delete in the rationale everything except the last sentence. | Wiedenmannott |  | Closed in origial Baseline document released
061109-20 | CP | T/V and 72205 | CSET0083 | Leave the word "background" in in the requirement section. Take ou the first sentence out of the rationale and O.K. to add the red to the rationale. Add the word Heat Flux in rationale? | Wiedenmannott |  | Closed in origial Baseline document released
061109-21 | CP | T/V and 72205 | CSET0122 | accept | Wiedenmannott |  | Closed in origial Baseline document released
061109-23 | CP | T/V and 72205 | CSET0086 | Reject | Wiedenmannott |  | Closed in origial Baseline document released
061109-24 | CP | T/V and 72205 | CSET0089 | accept | Wiedenmannott |  | Closed in origial Baseline document released
061109-25 | CP | T/V and 72205 | CSET0084 | Stop requirement at +-54. TBR is deleted. The rationale is This wil be measured by the control thermocouple measuring steady state conditions and based upon an uncertainty analysis using the square root of the sum of squares (RSS) method. | Wiedenmannott |  | Closed in origial Baseline document released
061109-26 | CP | T/V and 72205 | CSET0090 | accept | Wiedenmannott |  | Closed in origial Baseline document released
061109-27 | CP | T/V and 72205 | CSET0056 | accept | Wiedenmannott |  | Closed in origial Baseline document released
061109-28 | CP | Facilities and 72205 | CSET0102 | Only use the words in the quotes as the rationale | Wiedenmannott |  | Closed in origial Baseline document released
061109-29 | CP | Facilities and 72205 | CSET0104 | Reject | Wiedenmannott |  | Closed in origial Baseline document released
061109-30 | CP | Facilities and 72205 | CSET0116 | Reject | Wiedenmannott |  | Closed in origial Baseline document released
061109-31 | CP | Facilities and 72205 | CSET0117 | Fix title only | Wiedenmannott |  | Closed in origial Baseline document released
061109-32 | CP | Facilities and 72205 | CSET0007 | Change to the following: The SET shall ground transport the CEV test article with amaximum weight of 55000lbs within SPF. | Wiedenmannott |  | Closed in origial Baseline document released
061109-33 | CP | Facilities and 72205 | CSET0105 | Accept | Sorge/Wiedenmannott |  | Closed in origial Baseline document released
061109-34 | CP | Facilities and 72205 | CSET106 | In req. delter per NASA gRC… In rationale, Keep original black requirement and delete reference to GRC | Wiedenmannott |  | Closed in origial Baseline document released
061109-35 | CP |  | CSET0108 | Accept | Wiedenmannott |  | Closed in origial Baseline document released
061109-36 | CP |  | CSET0109 | Reject | Wiedenmannott |  | Closed in origial Baseline document released
061109-37 | CP |  | CSET0110 | This is a note that this requirement in not in the RLS. | Wiedenmannott |  | Closed in origial Baseline document released
061109-38 | CP | VTC EIS | VTC0047 | Change rationale shall to "assumes" It is assumed that the ACS requires no more than two test operators to control all noise sources. It is assumed that the ACS will be able to control……. | Weidenmannott |  | Closed in origial Baseline document released
061109-39 | CP |  |  | Create final From/To CSET Requirements to S. Wilson | Wiedenmannott | 2009-06-19 | Closed in origial Baseline document released
061109-40 | CP |  |  | Report number of TBR/TBDs in all documents (CSETs and EISs) | Wiedenmannott | 2009-07-01 | Closed in origial Baseline document released
6/19/2009 CP | [6 empty] | Closed in origial Baseline document released
061909-1 | CP | VTC EIS | p. 1.3 Change Authority | changed paragrapgh to reflect EIS document. | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-2 | CP | VTC EIS |  | Move 72205 from applicable to reference | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-3 | CP | VTC EIS | VTC 0009 | Reject | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-4 | CP | VTC EIS | VTC 0010 | Reject | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-5 | CP | VTC EIS | VTC 0012 | Reject | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-6 | CP | VTC EIS | VTC 0014 | Reject the sump is already in | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-7 | CP | VTC EIS | VTC 0122 | Reject already built | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-8 | CP | VTC EIS | VTC 0007 | Accept and add the word "true" between ft. and elevation. | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-9 | CP | VTC EIS | VTC 0008 | Reject | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-10 | CP | VTC EIS | VTC 0002 | Reject | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-11 | CP | VTC EIS | VTC 0018 | Reject | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-12 | CP | VTC EIS | VTC 0020 | Reject | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-15 | CP | VTC EIS | VTC 0079 | Reject | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-16 | CP | VTC EIS | VTC 0080 | Reject | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-17 | CP | VTC EIS | VTC 0044 | Acccept | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-18 | CP | VTC EIS | VTC 0042 | Reject | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-19 | CP | VTC EIS | VTC0037 | Accept and add the word "true" between ft. and elevation. | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-21 | CP | VTC EIS | VTC0123 | Accept | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-23 | CP | VTC EIS | VTC 0047 | Accept Ensure table has new number | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-24 | CP | VTC EIS | VTC 0048 | Reject | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-25 | CP | VTC EIS | VTC 0054 | Accept | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-26 | CP | VTC EIS | Figure 3.2.6-1 | Reject make sure figure stays as 3.2.6-1 | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-27 | CP | VTC EIS | VTC XXX (flowdown of CSET 0106) | Accpet chagne and Add NASA GRC Electrical Branch Design Guidelines to applicable document. Also delete "see verificaiton" | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-29 | CP | VTC EIS | VTC 0069 | Accept the deletion | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-30 | CP | VTC EIS | VTC 0070 | Accept | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-31 | CP | VTC EIS | VTC 0137 | Accept | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-32 | CP | VTC EIS | VTC 0072 | Reject | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-33 | CP | HSDAS EIS | 72205 | Reject | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-34 | CP | HSDAS EIS | Safety Manual | Add to Reference | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-35 | CP | HSDAS EIS | HSDAS 0002 | Reject but add rationale that state sthis applies to hsdas electronis and s/w and a second statement that typical requiremetnts do not meet the 30 year requirement. | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-36 | CP | HSDAS EIS | HSDAS 0003 | Reject | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-37 | CP | HSDAS EIS | HSDAS 0038 | Reject | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-39 | CP | HSDAS EIS | HSDAS XXXX (formally CSET 0066) | Accept (this is new req. to benham) | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-40 | CP | CSET Orphans |  | Need a list of CSET requirements that do not have a home or that are orphans. | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-41 | CP | Exceptions List |  | create an errata list (table)of requirements not applicable to benham i.e. thermocouples, that Benham is not responsible for | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-42 | CP | HSDAS EIS | HSDAS 0020 | Reject | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-43 | CP | VTC /HSDAS EIS | P. 2.1 REF. Docs. | Correct Project name (Space Environmental Test) | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-44 | CP | VTC /HSDAS EIS | P. 2.1 REF. Docs. | Add GRC-IET-PLN-002 | SE&I | 2009-06-25 | Closed in origial Baseline document released
061909-45 | CP | VTC /HSDAS EIS | P. 2.1 REF. Docs. | Add GRC -SET-PLN-004 | SE&I | 2009-06-25 | Closed in origial Baseline document released
7/2/2009 CP
070209-01 | CP | E3 EIS | 1.6 | Reference Project Plan not SEMP for Roles and Responsibilites | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-02 | CP | E3 EIS | 1.6.1-1.6.6 | remove and find somewhere else to put them | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-03 | CP | E3 EIS | 2.2 | Add Project Management Plan | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-04 | CP | E3 EIS | 2.1 | Move Safety Manueal to Applicable Documents | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-05 | CP | E3 EIS | 2.2 | Add GRC Occupational Health Program Manual and the GRC Environmental Manual | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-06 | CP | E3 EIS | 2.2 | Add "GRC" in front of SET-PLN-004 | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-07 | CP | E3 EIS | E3FT0006 | Leave as is next update change figure longitudal on page and show everything all in one figure later | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-08 | CP | E3 EIS | E3FT007 | Change Rationale: delete all except last sentence." Delete in requirement EEE words and ues E3 | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-09 | CP | E3 EIS | 8 | Leave as is | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-10 | CP | E3 EIS | 25 | Leave as is | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-11 | CP | E3 EIS | 26 | reword, or reference safety manual for RF escaping, or get #s etc. New Decision: Delete and Combine with E3FT0029. | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-12 | CP | E3 EIS | 11 | requirement must match the budget. Even though we agree technically, we need to have the requirement match budget. This requirement does not state empty chamber. requirement is good, the rationale needs to be changed to XXXX . Kurt and Nicole to work new rationale. Once more change (see M. Senchak)(change envirnmental to test and get rid of everything from and is tolerant | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-13 | CP | E3 EIS | 28 | Leave as is | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-14 | CP | E3 EIS | 12 | leave as is | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-15 | CP | E3 EIS | 29 | Combine with E3FT0026 and get rid of 26 make sure reference safety manual action from 26. Change 29 to state "All penetrations including doors through the …... | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-16 | CP | E3 EIS | 27 | Apply critical lift standard to this requirement. Add 8719.9 in applicable document and refernece in the requirement | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-17 | CP | E3 EIS | 15 | in rationale at end add" excluding polar crane" | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-18 | CP | E3 EIS | 17 | Leave as is | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-19 | CP | E3 EIS | 30 | insert 8719.9 (for factors of safety). Remove tbd and insert 8719.9 | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-20 | CP | E3 EIS | 4.1.3 | delete phasing, no more baseline 1 option and also delete in column for phasing in verfication matrix | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-21 | CP | E3 EIS | Acryonm List | Delete reference to IET | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-22 | CP |  |  |  | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-23 | CP | TVAC EIS | 1.6 | reference Project Plan instead of SEMP | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-24 | CP | TVAC EIS | 2.1 | Add Safety Manual to applicable Docs. | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-25 | CP | TVAC EIS | 1.1 | Change testing to test | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-26 | CP | TVAC EIS | 2.2 | delete refernce to CEV-T031000 | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-27 | CP | TVAC EIS | 2.2 | Add GRC Occupational Health Program Manual and the GRC Environmental Manual to applicable docs | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-28 | CP | TVAC EIS | 2.2 | Add GRC infront of SET-PLN-004 | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-29 | CP | TVAC EIS | 2.2 | change IET PLN 002 to SET PLN 002 | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-30 | CP | TVAC EIS | TVAC0002 | Make rationale same as e3 | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-31 | CP | TVAC EIS | TVAC0004 | delete clean and dry out. | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-32 | CP | TVAC EIS | TVAC0005 | Leave as is | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-33 | CP | TVAC EIS | TVAC0006 | Add a figure . Correct the spelling of envelope | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-34 | CP | TVAC EIS | TVAC0009 | Leave as is | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-35 | CP | TVAC EIS | TVAC0010 | Should be Thermal Heat Flux System in title. | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-36 | CP | TVAC EIS |  | Critical lift for Heat Flux structure issue needs to be an official action for Ludwiczak, Sorge and Speier to work . This will be updated in next updated version of this EIS and should not hold up the baseling today. | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-37 | CP | TVAC EIS | TVAC0011 | Delete : CEV Project-provided Add to rationale at the end " during the actual test CEV will provide the type t thermocouple signal" | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-38 | CP | TVAC EIS | TVAC0015 | Leave as is | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-39 | CP | TVAC EIS | TVAC0001 | Delete this requirement . We will keep 30 year and work verification later | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-40 | CP | TVAC EIS | 4.1.3 | delete and also column ant table | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-41 | CP | TVAC EIS | acronym list | delete IET | SE&I | 2009-07-14 | Closed in original Baseline releas
070209-44 | CP | Facility EIS | 2.1 | Add to applicable documents the two documents reference above. | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-45 | CP | Facility EIS | 2.1 | See M. Senchak | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-46 | CP | Facility EIS | 2.1 | Add "GRC" in from on SET-PLN-004 | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-47 | CP | Facility EIS | 2.1 | Change IET PLN 002 to SET PLN 002 | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-48 | CP | Facility EIS | TEST0001 | add dimensions | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-49 | CP | Facility EIS | 2 | Move to HSDAS | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-50 | CP | Facility EIS | 3 | delete | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-51 | CP | Facility EIS | 4 | delete | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-52 | CP | Facility EIS | 8 | Move to HSDAS EIS | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-53 | CP | Facility EIS | 7 | Move to HSDAS EIS | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-54 | CP | Facility EIS | 9 | Leave as is | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-55 | CP | Facility EIS | 10 | move to Test Wedge Doc. | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-56 | CP | Facility EIS | 11 | move to Test Wedge Doc. | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-57 | CP | Facility EIS | 3.2.7.4 | delete this paragraph | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-58 | CP | Facility EIS | 12 | Delete . Captured in TEST0033 | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-59 | CP | Facility EIS | 13 | move to Test Wedge Doc. | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-60 | CP | Facility EIS | 14 | R. Sorge provide figure and then change requirement to referene figure | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-61 | CP | Facility EIS | 15 | delete R. Sorge to review req. in VTC EIS | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-62 | CP | Facility EIS | 16 | delete R. Sorge to review req. in VTC EIS | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-63 | CP | Facility EIS | 17 | delete R. Sorge to review req. in VTC EIS | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-64 | CP | Facility EIS | 20 | Move to TVAC EIS | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-65 | CP | Facility EIS | 21 | Leave as is | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-66 | CP | Facility EIS | 22 | point to 3 pentrations R. Sorge to rewrite to look like 23. Defined in table (delete reference to ICD) | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-67 | CP | Facility EIS | 23 | delete, same as cSET90 in TVAC spec | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-68 | CP | Facility EIS | 24 | move to Test Wedge Doc. | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-69 | CP | Facility EIS | 57 | delete it's in the GAP but GAP has Lockheed number on it. R. Sorge to incorporate in the Site Support Plan | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-70 | CP | Facility EIS |  | R. Sorge to incorporate the above TEST 0057 requirement in his Site Support Plan | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-71 | CP | Facility EIS | 25 | Leave as is | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-72 | CP | Facility EIS | 26 | R. Sorge to provide new wording. Delete rationale | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-73 | CP | Facility EIS | 58 | change first sentence to state The SET shall provide a remote heated storage area, with 16 ft. wide by 16 ft. high access door, for test article crates, packing material and GSE. Delete last sentence in rationale. | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-74 | CP | Facility EIS | 27 | Leave as is | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-75 | CP | Facility EIS | 28 | Leave as is | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-76 | CP | Facility EIS | 29 | Leave as is | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-77 | CP | Facility EIS | 48 | Leave as is | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-78 | CP | Facility EIS | 50 | Change 30 ton to 20 ton. Change rationale to existing crane | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-79 | CP | Facility EIS | 59 | Leave as is | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-80 | CP | Facility EIS | 52 | move to Test Wedge Doc. | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-81 | CP | Facility EIS | 32 | Move to VTC R. Sorge to verifiy | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-82 | CP | Facility EIS | 33 | Leave as is | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-83 | CP | Facility EIS | 35 | Leave as is | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-84 | CP | Facility EIS | 36 | Delete covered in 37 | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-85 | CP | Facility EIS | 37 | Change weight from 110,000lbs to 125,000 lbs. | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-86 | CP | Facility EIS | 53 | Add to rationale this is sized to support thermal vacum and thermal valance testing | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-87 | CP | Facility EIS | 38 | move to Test Wedge Doc. | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-88 | CP | Facility EIS | 39 | Delete second half of rationale. Take out both in rationale and delete after operating permit. | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-89 | CP | Facility EIS | 40 | Leave as is | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-90 | CP | Facility EIS |  | Definition of reviews needs to be defined in SEMP and S. Motil and R. Wiedenmannott working ORR, Acceptance etc. | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-91 | CP | Facility EIS | 43 | move to Test Wedge Doc. | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-92 | CP | Facility EIS | 44 | move to Test Wedge Doc. | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-93 | CP | Facility EIS | 45 | move to Test Wedge Doc. | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-94 | CP | Facility EIS | 46 | move to Test Wedge Doc. | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-95 | CP | Facility EIS | 47 | Leave as is | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-96 | CP | Facility EIS | 4.1.3 | Delete phaseing and delete phasing colum in verification plan | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-97 | CP | Facility EIS | CSET 21 | remove in VTC spec | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-98 | CP | Facility EIS | CSET 3 | remove in VTC Spec | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-99 | CP | Facility EIS | CSET 125 | remove in VTC Spec | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-100 | CP | Facility EIS | CSET 102 | Leave as is | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-101 | CP | Facility EIS | CSETE 103 | If in VTC, remove from here | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-102 | CP | Facility EIS | CSET 0029 | remove in VTC | SE&I | 2009-07-14 | Closed in orginal baseline release
070209-103 | CP | Facility EIS |  | R. Sorge, M. Senchak and S. Motil to review the CSET requirements and determine if they need to stay in this document if they are called out elsewhere. Should keep requirement if don' have costs to cover it. | SE&I | 2009-07-14 | Closed in orginal baseline release
7/2/09 CP |  | VTC EIS
070209-01 | CP |  |  | Write change request to document decisions made | SE&I/ M Senchak | 2009-07-13 | Closed - SET CR 001 and SET CR 002
7/23/09 CP
072309-01 | CP | VCON ERB Recommendation
072309-02 | CP |  |  | Find out from Benham how they intend to meet the HSDAS requirements without a COLA signal | A. Hozman |  | closed, Per A. Linne, these items were worked and settled out of board and reported to the project manager
072309-03 | CP |  |  | Reinstate MVF working group and initiate disussions on system stabilities | A. Hozman |  | closed, Per A. Linne, these items were worked and settled out of board and reported to the project manager
072309-04 | CP |  |  | Find out from Benham why philosphies are different for MVF vs. RATF, with regard to spatial averaging | A. Hozman |  | closed Per A. Linne, these items were worked and settled out of board and reported to the project manager
072309-05 | CP | SET PROJECT PLAN |  | Add "Table Top" definition. Provide to F Elliott by cob 7/27/09 | A Linne | 2009-07-27 | closed
072309-06 | CP |  |  | Add Technical Metrics in Table 4. Provide to F Elliott | A Linne | 2009-07-27 | closed
072309-07 | CP |  |  | Update section 3.14 to include the Facility Security Plan - Provide verbiage to F Elliott | R Sorge | 2009-07-27 | closed
072309-08 | CP |  |  | Add "Insight" and "Oversight" definition prior to 7/30/09 CP | F Elliott | 2009-07-29 | closed
072309-09 | CP |  |  | Correct Waiver Log per NPR 7120.5D prior to 7/30/09 CP | F Elliott | 2009-07-29 | closed
072309-10 | CP |  |  | Define ORR vs. Test Readiness Reviews etc milestones. A Linne to set up a meeting with SE&I, CE, PM and Facility Operations to resolve prior to 7/30/09 CP | A Linne | 2009-07-29 | closed
072309-11 | CP |  |  | Provide updated procurement numbers for E3 and Tvac in Table 5 | N Smith |  | closed
8/10/09 Independent Assessment |  |  |  |  | S. Motil
081009-IA01 | OTHER | Tech R1 |  | Conduct a Concept of Test Operations TIM in the near term including all involved parties to establish agreed upon baseline; then document in a Test ConOps. | S. Motil |  | Orion action. SET is in need of the Con Ops for planning facility operations. There are SET Project risks in IRMA that are directly impacted by the Orion Con Ops.
081009-IA02 | OTHER | Tech R2 |  | Orion Project should finalize key potential requirements drivers in the near term, prioritizing those that affect the core facility. | S. Motil |  | Orion action. SET has a core set of requirements that are in the baseline cost. Further changes will incur cost and schedule on SET.
081009-IA03 | OTHER | Tech R3 |  | Continue to track RATF development as a key Orion/SET Project risk and look for risk mitigation opportunities. | S. Motil |  | Agree. There are currently risks in the system for RATF development, and are tracked and updated monthly through the SET Risk Review Panel.
|  |  |  | •Use of a pathfinder test article during early chamber checkout. |  |  | •Current pathfinder is a NASA GRC provided Verification Test Article and wil be tracked on Benham schedule with regular status from NASA to Benham..
|  |  |  | •Early checkout of equipment going into chamber to ensure they can withstand the environment (lights, paint, etc.) |  |  | •Agree. Products selected will be for harsh environments. Plans have not been completely vetted, but checkout is accounted for.
|  |  |  | •Check out the acoustic control system with multiple horns/modulators as practical. |  |  | •Agree. Multiple tests and analyses are planned throughout the development of the RATF.
|  |  |  | •Continue involvement of independent acoustic experts post FY09; particularly when acoustic chamber is being checked out and commissioned. May not be full-time, with a shift in expertise to experienced acoustics chamber operators. |  |  | •Budget does not currently account for the continued involvement of acoustic experts beyond FY09. Additional resources would be required.
081009-IA04 | OTHER | Tech R4 |  | Conduct a hazards assessment and examine RATF crane implementation approaches that mitigate the risk of qualification hardware damage. | S. Motil |  | Orion action. Hazards assessment to be performed by Orion along with optional scenarios for fairing removal and installation.
081009-IA05 | OTHER | Tech R5 |  | Establish clear ownership for the GN2 evaporator fuel supply. | S. Motil |  | Ownership has been established. Plum Brook Station has been working the supply.
081009-IA06 | OTHER | Tech R6 |  | Ensure data channel capability is understood and acceptable | S. Motil |  | Agree. Current SET budget accounts for controllable data channel capability (32 channels total; 10 available for hardware provider), but is not yet confirmed as being sufficient by Lockheed-Martin. Orion T&V should lead resolution of requirement and SET will support as required.
081009-IA07 | OTHER | Tech R7 |  | Consider alternative methods for handling the cryo shrouds based on accommodating the entire test operations scenario. •Should they be placed in containers/crates and moved to storage rather than hung on walls? | S. Motil |  | SET is currently assessing methods for handling the cryo shrouds. However, an Orion ConOps is needed.
081009-IA08 | OTHER | Tech R8 |  | Track the SET E3 design as a top SET Project Risk and continue to pursue risk mitigation activities. Establish the baseline E3 requirements in the relatively near term. | S. Motil |  | Agree. SET has baseline requirements for E3. Orion action to modify requirements if the facility is not meeting their needs. There are risks in the system that address requirements for E3.
081009-IA09 | OTHER | Tech R9 |  | Establish the test operations flow for E3 testing; consider strongly the preferred technical approach of conducting E3 testing last followed by a lightning test. | S. Motil |  | Agree. Orion action – ConOps development.
081009-IA10 | OTHER | Tech R10 |  | Characterize the impacts of cryo shrouds on E3 testing as early as practical and/or address alternative approaches to handling the cryo shrouds to eliminate the impact. | S. Motil |  | Agree. SET is currently addressing the impact of cryo shrouds on E3 testing.
081009-IA11 | OTHER | Tech R11 |  | Examine ways to accelerate E3 facility commissioning and/or mitigate risks earlier than the current schedule. | S. Motil |  | Agree and currently assessing ways to accelerate commissioning.
081009-IA12 | OTHER | Tech R12 |  | Look for ways to implement pathfinder activities as early in the flow as practical to uncover issues prior to the start of qualification testing. | S. Motil |  | Agree. SET is currently developing a Verification Test Article to use for commissioning of the VTC and for familiarity with handling hardware.
081009-IA13 | OTHER | Tech R13 |  | Analyze the schedule/cost risks of failure of critical equipment as part of sparing planning to determine areas where funding for critical spares is warranted. Consider optimum timing for purchasing spares based on reliability, lead time-away, availability, and cost considerations. | S. Motil |  | Agree. Benham is on contract to develop a Spare Parts List that includes schedule and cost risks as well as procurement times. Although no spares will be procured as part of the baseline plan.
081009-IA14 | OTHER | Tech R14 |  | Trade the cost of paying for a security system with sufficiency of providing guards as required; the security system costs do not appear to be warranted. | S. Motil |  | Agree. Orion action.
081009-IA15 | OTHER | CoF R1 |  | GRC to continue to fund institutional CoF’s as appropriate. | S. Motil |  | Agree
•These protect the Programs investment in the SPF and maintain technical capability for the future.
081009-IA16 | OTHER | CoF R2a |  | •The construction industry has many evaluation tools which can take the temperature of the project to quantitatively and qualitatively assess the project health and integrated team alignment | S. Motil |  | Agree. Development of project metrics is in process as part of project plan finalization. Orion determining frequency of reporting. GRC management briefed at SMC, bi-weekly to Deputy Director/Spaceflight Systems Management and weekly to Facilities Directorate.
081009-IA17 | OTHER | CoF R2b |  | Establish Incentives and performance agreements | S. Motil |  | Agree. Cost sharing intended to be part of renegotiated contract
| OTHER |  |  | •Team performance on both sides relative to process flow, scheduling and cost goals needs to be pre-negotiated and understood
081009-IA18 | OTHER | CoF R2c |  | Refine critical communications and processes flows | S. Motil |  | Agree. Project precesses are still being developed and refined.
| OTHER |  |  | •The RFI and shop drawing processes need to be defined and negotiated.
| OTHER |  |  | •Include analysis of the approval cycles
081009-IA19 | OTHER | CoF R2d |  | Establish highly visible metrics | S. Motil |  | Agree. Metrics being defined in project plan.
| OTHER |  |  | •Recommend the selection of 6 problem areas and choose a representative metric which can be displayed on the walls of the team and mentioned at each status meeting. I.e., total days for a shop drawing review, amount of rework, problems arriving at an ERB, etc.
081009-IA20 | OTHER | CoF R3 |  | “Drain the Swamp” to find hidden engineering issues and resolve them | S. Motil |  | Agree. Chief Engineer actively involved with the team and meets regularly to identify and resolve issues. Issues discussed with project management team on a regular basis.
081009-IA21 | OTHER | CoF R4 |  | Define in contractual and engineering terms what constitutes success or acceptance criteria. Jointly develop this information with the contractor | S. Motil |  | Agree. Engineering team is currently working with the contractor to develop, jointly, success criteria. Alpha contracting will continue through the proposal phase. Verification plans are jointly worked prior to contract delivery.
081009-IA22 | OTHER | CoF R5 |  | Allow GRC to program an appropriate percentage of the estimate to complete in the FY10 amount | S. Motil |  | Orion decision. SET has programmed enough funding to make it through FY10 Op Planning.
•SET must return for a FY10 Op Plan Change anyway
•SET has enough authority and funding to easily make it to then
081009-IA23 | OTHER | CoF R6 |  | Revise IRMA 4432 to be consistent with the project realignment | S. Motil |  | Orion Decision
| OTHER |  |  | Recommend that this risk be moved to a Top CxP risk
081009-IA24 | OTHER | CoF R7 |  | Recommend that an assessment of risks by each facility subsystem be performed as soon as possible and well prior to the start of the test campaign | S. Motil |  | Agree. SET is currently assessing risks and plan to have updated with cost threats by September 5, 2009.
081009-IA25 | OTHER | CoF R8 |  | Recommend implementation of monthly redline reviews | S. Motil |  | Agree. Part of project processes still in work.
081009-IA26 | OTHER | CoF R9 |  | Recommend weekly schedule coordination meetings to align the personnel, deliverables and check progress to track progress and identify future problems in time to resolve them. | S. Motil |  | SET is already performing bi-weekly schedule reviews. At this time, the project will continue with every other week.
081009-IA27 | OTHER | CoF R10a |  | Visibly track and report problems which occur outside of established performance norms | S. Motil |  | Agree. SET has processes in place to track problems.
081009-IA28 | OTHER | CoF R10b |  | COTR should have a written delegation with an established level of authority to keep the work moving day to day | S. Motil |  | Agree. Until the project has demonstrated progress, SET project management will retain control of the budget. This is a good idea, but SET is not yet ready to relinquish budget authority.
081009-IA29 | OTHER | CoF R10c |  | Jointly establish 12 – 20 significant milestones and visibly track results | S. Motil |  | Agree. SET has a list of milestones that are tracked.
081009-IA30 | OTHER | Cont R1a |  | Provide an aggressive cost share to encourage the contractor to underrun | S. Motil |  | Agree. SET has coordinated approach with Deputy Center Director and procurement to establish cost share prior to negotiations.
•Currently proposing 70/30, but consider 50/50 (like original contract)
•Future projected underrun could be used to offset future cost needs (spares) and possibly mitigate need for reserves
081009-IA31 | OTHER | Cont R1b |  | No identified schedule incentives | S. Motil |  | Agree. SET has coordinated approach with Deputy Center Director and procurement to establish cost share prior to negotiations.
•Probably due to the large margin available
•Should consider some contract adjustment to allow the contractor to trade cost incentive against schedule margin
081009-IA32 | OTHER | Cont R2 |  | Implement a below threshold change clause | S. Motil |  | Agree. See CoF R10b response.
•Clause will allow time and schedule efficient implementation of out-of-scope changes
•Probably a threshold of $30k - $40k
•Use board process to approve before implementing the change and fence budget
081009-IA33 | OTHER | Cont R3 |  | COTR should immediately develop this plan and baseline through the board process | S. Motil |  | GRC does not require surveillance plans. Although, SET agrees the plan is needed.
•Plan should identify surveillance requirements for the contract activities more challenging than typical CoF projects
•Update plan once modification 15 is definitized
081009-IA34 | OTHER | Cont R4 |  | Clean up paperwork of changes | S. Motil |  | Agree
•Difficult to see where change was definitized or a UCA
•Appears RFI’s were implemented with NTE’s or estimates but no clear trace to a UCA
081009-IA35 | OTHER | Cost R1 |  | Include appropriate CoF contingency for remaining construction | S. Motil |  | Orion decision
081009-IA36 | OTHER | Cost R2 |  | Open IRMA Cost Risk that addresses the $5.58M potential cost increase as deleted content may be required | S. Motil |  | Disagree. SET has provided GRC senior management with the overall implementation plan. The engineering team reduced content, but also indicated that their reduced budget/content was a workable plan.
081009-IA37 | OTHER | Cost R3 |  | SET Project should address discrepancies with Benham and obtain correction or adequate explanation | S. Motil |  | Agree
081009-IA38 | OTHER | PM R1a |  | Develop a fully integrated schedule across both NASA (CoF and In-house work) and the contractor, or | S. Motil |  | Disagree. There will be a level of integration between the two schedules. SET will not fully integrate the Benham schedule, but will choose milestones to link to.
081009-IA39 | OTHER | PM R1b |  | Increase schedule reporting within the Project to account for the lack of schedule integration | S. Motil |  | Disagree that there is a lack of schedule integration. Schedule reporting is done on a bi-weekly basis with the SET team. The contractor is required to submit schedule updates on a monthly basis.
081009-IA40 | OTHER | PM R2 |  | Report status of schedule float to Orion Project Manager on a regular basis (monthly) | S. Motil |  | Agree. But will work with Orion on their needs.
|  |  |  | •Necessary on a project of this complexity with a challenging schedule (option A | S. Motil
8/12/2009 ERB
081209-09 | ERB |  |  | Schedule Reconvene | K. Kachmar | 2009-08-21 | Closed, Scheduled for August 21, 2009, Defreed scheduled for September 11, 2009
9/8/2009 VTA EIS
090809-10 | ERB | VTA005 |  | O.K. as is no action | R. Wiedenmannott |  | Closed
090809-11 | ERB | VTA007 |  | O.K. as is no action | R. Wiedenmannott |  | Closed
090809-22 | ERB | VTA017 |  | O.K. as is do not incorporate the red | R. Wiedenmannott |  | Closed
090809-23 | ERB | VTA018 |  | O.K. as is do not incorporate the red | R. Wiedenmannott |  | Closed
090809-24 | ERB | VTA019 |  | O.K. as is no action | R. Wiedenmannott |  | Closed
8/12/2009 ERB |  | SEMP ERB
081209-01 | ERB | SEMP | SCOPE | Refert to the Project Plan in Scope | SE&I | 2009-08-21 | Open
081209-02 | ERB |  |  | Work with T&V Office concerning reviews | SE&I | 2009-08-21 | Open
081209-03 | ERB |  |  | Review the Orion T&V SEMP for the roles of Lockheed Martin, GRC and the T/V Office | SE&I | 2009-08-21 | Open
081209-04 | ERB |  |  | Define how tabletop and carpet reviews wil be conducted and how they will meet the intent of PDR/CDRS to satisfy 7123.5 due to the uniqueness of this project | SE&I | 2009-08-21 | Open
081209-05 | ERB |  |  | Define inhouse work explicitly , ICDs (internal/external, I/F requirements, review planning, verificaiton plan and process, validation (what are we doing) and prodcut integraiton | SE&I | 2009-08-21 | Open
081209-06 | ERB |  |  | Signature Page shoul follow the GLP - Directorate Heads | SE&I | 2009-08-21 | Open
081209-07 | ERB |  |  | Rewrite the purpose and scope 1.1 and 1.2 | SE&I | 2009-08-21 | Open
081209-08 | ERB |  |  | K. Kachmar report on the usage, clasificaiton of SBU data | K. Kachmar | 2009-08-21 | Open
2009-09-09 |  | MVF VTA Design ERB
09092009-01 | ERB |  |  | T. Griebel to work with M. Freedman, Karl B. , Bob Sefcik on the chart showing CS labor and materials for all three options and have ready by noon tomorrow. | T. Griebel | 2009-09-10 | open
09092009-02 | ERB |  |  | M. Freedman update with new charts showing deltas based on the new numbers from T. Griebal and Mark Sefcik for all three options and show deltas from the 358K. | M. Freedman | 2009-09-10 | open
2009-09-11 | CP | VTA EIS ERB Recommendation
09112009-01 |  |  |  | Update the signature page to e consistent with the other EIS documents |  |  | 9/16/09 Waiting to hear back from R. Wiedenmannott on questions with newly supplied version which incorporates this action.
09112009-02 |  |  |  | Update cross reference matrix when released and produced from cradle. |  |  | 9/16/09 Waiting to hear back from R. Wiedenmannott on questions with newly supplied version which incorporates this action.
09112009-03 |  |  |  | Requirement VTA0004 needs to include rationale accommodating 43' crane height to enable transfer thru Tvac doors |  |  | 9/16/09 Waiting to hear back from R. Wiedenmannott on questions with newly supplied version which incorporates this action.
9/8/2009 V | ERB | VTA EIS ERB
090809-01 | ERB |  |  | 2.2 Change the Reference section to only include the 3 deleted S | R. Wiedenmannott |  | Closed in initail Baseline VTA Document
090809-02 | ERB |  |  | 2. 0 Applicable Documents Keep 8719.9 in applicable put the rest in reference. | R. Wiedenmannott |  | Closed in initail Baseline VTA Document
090809-03 | ERB |  |  | Para 3.1.1 Keep the 1st two sentences, delete the rest. | R. Wiedenmannott |  | Closed in initail Baseline VTA Document
090809-04 | ERB |  |  | Para 3.2.6 Change title to Test Coordinate System and replace picture with cylinder and coordinate system. | R. Wiedenmannott |  | Closed in initail Baseline VTA Document
090809-05 | ERB | VTA0001 |  | Delete this requirement, this is a design solution | R. Wiedenmannott |  | Closed in initail Baseline VTA Document
090809-06 | ERB | VTA0002 |  | Delete this requirement, this is a design solution | R. Wiedenmannott |  | Closed in initail Baseline VTA Document
090809-07 | ERB | VTA0003 |  | O.K. as is no action | R. Wiedenmannott |  | Closed in initail Baseline VTA Document
090809-08 | ERB |  |  | Add to para 3.1.1 in the Definition of VTA which is All hardware that interfaces with thte MVF Shaker Table. VTA needs to include allh/w attached to the MVF table (See. R. Wiedenmannott) | R. Wiedenmannott |  | Closed in initail Baseline VTA Document
090809-09 | ERB | VTA004 |  | chagne 1000 lbs.to 3750lbs (5%) also in the rationale | R. Wiedenmannott |  | Closed in initail Baseline VTA Document
090809-12 | ERB | VTA008 |  | Delete | R. Wiedenmannott |  | Closed in initail Baseline VTA Document
090809-13 | ERB | VTA009 |  | Delete | R. Wiedenmannott |  | Closed in initail Baseline VTA Document
090809-14 | ERB | VTA010 |  | Delete | R. Wiedenmannott |  | Closed in initail Baseline VTA Document
090809-15 | ERB | VTA011 |  | Should read: The VTA shall be structurally designed to withstand a vibration input at the cg of at least 3.0 g in the lateral direction. Change rationale to " Defined as the +- Y and +- Z directions in Figure 3.2.6-1. Test aretical must be able to withstand a hard stop 3.0g" . Change title to "VTA Lateral Design Loads" See M. Senchak on rationale | R. Wiedenmannott |  | Closed in initail Baseline VTA Document
090809-16 | ERB | VTA012 |  | should read: The VTA shall be structurally designed to withstand a vibraiton input at the cg of a tleas 3.0 g in the vertical direction. Change Rationale to Defined as the +- X direction in Figure 3.2.6-1. . Change title to " VTA Vertical Design Loads" | R. Wiedenmannott |  | Closed in initail Baseline VTA Document
090809-17 | ERB | VTA013 |  | Delete | R. Wiedenmannott |  | Closed in initail Baseline VTA Document
090809-18 | ERB | VTA014 |  | Delete | R. Wiedenmannott |  | Closed in initail Baseline VTA Document
090809-19 | ERB | VTA015 |  | Change" The VTA transportation segments shall be designed to survive a maximum transportaion static load of 5 g's in the vetical direction and 3 g's in the lateral direction, not applied simutaneously. Rationale should state: This is a static load for the VTA segments during transportaiton | R. Wiedenmannott |  | Closed in initail Baseline VTA Document
090809-20 | ERB | VTA016 |  | Delete | R. Wiedenmannott |  | Closed in initail Baseline VTA Document
090809-25 | ERB | VTA020 |  | Delete | R. Wiedenmannott |  | Closed in initail Baseline VTA Document
8/10/09 CP
081009-01 | CP | GRC-SET-PLN-001 |  | S. Motil/F. Elliott to forward for signatures from the Orion project office | S.Motil/F. Elliot |  | OPEN, signature process external to SET CM/ 9/-18-09 Approved at GRC PRB. S. Motil to forward to Orion for signature, Closed, S. Motil Forwarded to Orion for signature.
7/2/2009 CP
070209-42 | CP | Facility EIS | faCILITY ies |  | SE&I | 2009-07-14
070209-43 | CP | Facility EIS | 1.5 | Add GRC Occupational Health Program Manual and the GRC Environmental Manual | SE&I | 2009-07-14
6/11/2009 CP
061109-22 | CP | T/V and 72205 | CSET0085 | Removed from TVAC Duplicate to CSET0083. Need to work with Scott | Wiedenmannott |  | Theremal Heat Fux Structure
061909-13 | CP | VTC EIS | VTC 0075 | Reject | SE&I | 2009-06-25 | lets look at estop design and limitiations and make change in future. We want them to design estop for CEV Test article. We can state in verification plan how and what they are using.
061909-14 | CP | VTC EIS | VTC 0078 | Reject | SE&I | 2009-06-25 | Reject even though violates req. writing with multiple req.
061909-20 | CP | VTC EIS | VTC00130 | Accept Change ,and spell out BCD and change rationale to state pattern 1 ihas the same bolt circle as MVF and delete. Delete reference to 72205 | SE&I | 2009-06-25 | Work this requirement if need to change write a CR later
| CP | RATF ACS ERB Recommendation
09112009-04 |  |  |  | Proceed with procurement and NRC ACS development testing to occur early October 2009.
8/10/09 Independent Assessment
081009-IA01 | OTHER | Tech R1 |  | Conduct a Concept of Test Operations TIM in the near term including all involved parties to establish agreed upon baseline; then document in a Test ConOps. | S. Motil |  | Orion action. SET is in need of the Con Ops for planning facility operations. There are SET Project risks in IRMA that are directly impacted by the Orion Con Ops. 10/13/09 C CLOSED completed last week
081009-IA03 | OTHER | Tech R3 |  | Continue to track RATF development as a key Orion/SET Project risk and look for risk mitigation opportunities. | S. Motil |  | Agree. There are currently risks in the system for RATF development, and are tracked and updated monthly through the SET Risk Review Panel. 10/13/09 CLOSE. This is being worked as normal course of business. SET tracks risks through IRMA and reports at Orion Risk Board
|  |  |  | •Use of a pathfinder test article during early chamber checkout. |  |  | •Current pathfinder is a NASA GRC provided Verification Test Article and wil be tracked on Benham schedule with regular status from NASA to Benham..10/13/09 CLOSED. Worked through normal course of business.
|  |  |  | •Early checkout of equipment going into chamber to ensure they can withstand the environment (lights, paint, etc.) |  |  | •Agree. Products selected will be for harsh environments. Plans have not been completely vetted, but checkout is accounted for.
|  |  |  | •Check out the acoustic control system with multiple horns/modulators as practical. |  |  | •Agree. Multiple tests and analyses are planned throughout the development of the RATF. 10/13/09 CLOSED. Worked through normal course of business.
|  |  |  | •Continue involvement of independent acoustic experts post FY09; particularly when acoustic chamber is being checked out and commissioned. May not be full-time, with a shift in expertise to experienced acoustics chamber operators. |  |  | •Budget does not currently account for the continued involvement of acoustic experts beyond FY09. Additional resources would be required. 10/13/09 CLOSED. Worked through normal course of business.
081009-IA04 | OTHER | Tech R4 |  | Conduct a hazards assessment and examine RATF crane implementation approaches that mitigate the risk of qualification hardware damage. | S. Motil |  | Orion action. Hazards assessment to be performed by Orion along with optional scenarios for fairing removal and installation. 10/13/09 CLOSED This is an Orion Action
081009-IA06 | OTHER | Tech R6 |  | Ensure data channel capability is understood and acceptable | S. Motil |  | Agree. Current SET budget accounts for controllable data channel capability (32 channels total; 10 available for hardware provider), but is not yet confirmed as being sufficient by Lockheed-Martin. Orion T&V should lead resolution of requirement and SET will support as required. 10/13/09 CLOSED This is an Orion Action to track.
081009-IA05 | OTHER | Tech R5 |  | Establish clear ownership for the GN2 evaporator fuel supply. | S. Motil |  | Ownership has been established. Plum Brook Station has been working the supply. 10/13/09 CLOSED it has been established and Plum Brook is the owner.
081009-IA09 | OTHER | Tech R9 |  | Establish the test operations flow for E3 testing; consider strongly the preferred technical approach of conducting E3 testing last followed by a lightning test. | S. Motil |  | Agree. Orion action – ConOps development. 10/13/09 CLOSED This is an Orion Action
081009-IA14 | OTHER | Tech R14 |  | Trade the cost of paying for a security system with sufficiency of providing guards as required; the security system costs do not appear to be warranted. | S. Motil |  | Agree. Orion action.10/13/09 Closed. There will be no security system with guards.
081009-IA15 | OTHER | CoF R1 |  | GRC to continue to fund institutional CoF’s as appropriate. | S. Motil |  | Agree 10/13/09 Close as normal course of business
|  |  |  | •These protect the Programs investment in the SPF and maintain technical capability for the future. |  |  | 10/13/09 Close as normal course of business
081009-IA16 | OTHER | CoF R2a |  | •The construction industry has many evaluation tools which can take the temperature of the project to quantitatively and qualitatively assess the project health and integrated team alignment | S. Motil |  | Agree. Development of project metrics is in process as part of project plan finalization. Orion determining frequency of reporting. GRC management briefed at SMC, bi-weekly to Deputy Director/Spaceflight Systems Management and weekly to Facilities Directorate.10/13/09 Close will be handled through normal course of business.
081009-IA17 | OTHER | CoF R2b |  | Establish Incentives and performance agreements | S. Motil |  | Agree. Cost sharing intended to be part of renegotiated contract. 10/13/09 Close will be handled through normal course of business.
| OTHER |  |  | •Team performance on both sides relative to process flow, scheduling and cost goals needs to be pre-negotiated and understood |  |  | 10/13/09 Close will be handled through normal course of business.
081009-IA18 | OTHER | CoF R2c |  | Refine critical communications and processes flows | S. Motil |  | Agree. Project precesses are still being developed and refined.10/13/09 Close will be handled through normal course of business.
| OTHER |  |  | •The RFI and shop drawing processes need to be defined and negotiated. |  |  | 10/13/09 Close, overcome by events. Now have carpet tops for design dwgs.
| OTHER |  |  | •Include analysis of the approval cycles |  |  | 10/13/09 Close will be handled through normal course of business.
081009-IA22 | OTHER | CoF R5 |  | Allow GRC to program an appropriate percentage of the estimate to complete in the FY10 amount | S. Motil |  | Orion decision. SET has programmed enough funding to make it through FY10 Op Planning. 10/13/09 Closed, Orion said no
•SET must return for a FY10 Op Plan Change anyway
•SET has enough authority and funding to easily make it to then
081009-IA23 | OTHER | CoF R6 |  | Revise IRMA 4432 to be consistent with the project realignment | S. Motil |  | Orion Decision 10/13/09 Close Risk Geyer does not want Cof F reserves
| OTHER |  |  | Recommend that this risk be moved to a Top CxP risk
081009-IA24 | OTHER | CoF R7 |  | Recommend that an assessment of risks by each facility subsystem be performed as soon as possible and well prior to the start of the test campaign | S. Motil |  | Agree. SET is currently assessing risks and plan to have updated with cost threats by September 5, 2009. 10/13/09 Closed, scheduling regularly.
081009-IA26 | OTHER | CoF R9 |  | Recommend weekly schedule coordination meetings to align the personnel, deliverables and check progress to track progress and identify future problems in time to resolve them. | S. Motil |  | SET is already performing bi-weekly schedule reviews. At this time, the project will continue with every other week. 10/13/09 Closed, have regular shcedule meeitngs
081009-IA27 | OTHER | CoF R10a |  | Visibly track and report problems which occur outside of established performance norms | S. Motil |  | Agree. SET has processes in place to track problems. 10/13/09 Close, have a process for this
081009-IA28 | OTHER | CoF R10b |  | COTR should have a written delegation with an established level of authority to keep the work moving day to day | S. Motil |  | Agree. Until the project has demonstrated progress, SET project management will retain control of the budget. This is a good idea, but SET is not yet ready to relinquish budget authority. 10/13/09, Close, Work through normal course of business.
081009-IA30 | OTHER | Cont R1a |  | Provide an aggressive cost share to encourage the contractor to underrun | S. Motil |  | Agree. SET has coordinated approach with Deputy Center Director and procurement to establish cost share prior to negotiations. 10/13/09 Close, this is overcome by events. Mod 16 is now signed and in place
|  |  |  | •Currently proposing 70/30, but consider 50/50 (like original contract) |  |  | 10/13/09 Close, this is overcome by events. Mod 16 is now signed and in place
|  |  |  | •Future projected underrun could be used to offset future cost needs (spares) and possibly mitigate need for reserves |  |  | 10/13/09 Close, this is overcome by events. Mod 16 is now signed and in place
081009-IA31 | OTHER | Cont R1b |  | No identified schedule incentives | S. Motil |  | Agree. SET has coordinated approach with Deputy Center Director and procurement to establish cost share prior to negotiations.10/13/09 Close, this is overcome by events. Mod 16 is now signed and in place
|  |  |  | •Probably due to the large margin available |  |  | 10/13/09 Close, this is overcome by events. Mod 16 is now signed and in place
|  |  |  | •Should consider some contract adjustment to allow the contractor to trade cost incentive against schedule margin |  |  | 10/13/09 Close, this is overcome by events. Mod 16 is now signed and in place
081009-IA32 | OTHER | Cont R2 |  | Implement a below threshold change clause | S. Motil |  | Agree. See CoF R10b response. 10/13/09 Close, this is overcome by events. Mod 16 is now signed and in place
|  |  |  | •Clause will allow time and schedule efficient implementation of out-of-scope changes |  |  | 10/13/09 Close, this is overcome by events. Mod 16 is now signed and in place
|  |  |  | •Probably a threshold of $30k - $40k |  |  | 10/13/09 Close, this is overcome by events. Mod 16 is now signed and in place
|  |  |  | •Use board process to approve before implementing the change and fence budget |  |  | 10/13/09 Close, this is overcome by events. Mod 16 is now signed and in place
081009-IA35 | OTHER | Cost R1 |  | Include appropriate CoF contingency for remaining construction | S. Motil |  | Orion decision 10/13/09 Closed. Geyer does not want CofF reserves.
081009-IA36 | OTHER | Cost R2 |  | Open IRMA Cost Risk that addresses the $5.58M potential cost increase as deleted content may be required | S. Motil |  | Disagree. SET has provided GRC senior management with the overall implementation plan. The engineering team reduced content, but also indicated that their reduced budget/content was a workable plan. 10/13/09 closed
081009-IA37 | OTHER | Cost R3 |  | SET Project should address discrepancies with Benham and obtain correction or adequate explanation | S. Motil |  | Agree. 10/13/09 Close, beign done through normal course of business.
081009-IA38 | OTHER | PM R1a |  | Develop a fully integrated schedule across both NASA (CoF and In-house work) and the contractor, or | S. Motil |  | Disagree. There will be a level of integration between the two schedules. SET will not fully integrate the Benham schedule, but will choose milestones to link to. 10/13/09 Close
081009-IA39 | OTHER | PM R1b |  | Increase schedule reporting within the Project to account for the lack of schedule integration | S. Motil |  | Disagree that there is a lack of schedule integration. Schedule reporting is done on a bi-weekly basis with the SET team. The contractor is required to submit schedule updates on a monthly basis. 10/13/09 Close
081009-IA40 | OTHER | PM R2 |  | Report status of schedule float to Orion Project Manager on a regular basis (monthly) | S. Motil |  | Agree. But will work with Orion on their needs.10/13/09 Close, part of TCSR
|  |  |  | •Necessary on a project of this complexity with a challenging schedule (option A | S. Motil |  | 10/13/09 Close, part of TCSR
2009-09-08 | ERB | VTA EIS ERB
090809-21 | ERB |  |  | M. Freedman work with K. Shupp to put SET risk in system | M. Freedman |  | 10/13/09 Closed per K. Shupp
2009-10-01 | CP
10012009-01 |  | SET-PLN-005 |  | T. Best to provide K. Kachmar with updated document for signature | Best |  | Closed 10/13/09
10012009-02 |  | SET-PLN-005 |  | T. Best to work with R. Sorge and agree on verbiage for section 8. 2. | Best/Sorge |  | Closed 10/13/09 T. Best Email

## Resource List
Power 4 Pink -Patient Advocate Committee Resource List
Resource | Name | Address | Phone # | Resources Provided
Financial Assistance | Power 4 Pink, Inc. | P.O. Box 1034 Amherst, OH 44001 | 4406543487 | Provides financial assistance for Lorain County breast cancer survivors whose income is less than 300% of the poverty level who are currently in treatment. Website: www.power4pink.com
| JD Breast Cancer Foundation | 14837 Detroit Ave #295 Cleveland, Oh 44107 | 2167919447 | Organizations offering ground transportation assistance for cancer patients and/or family members. Provides financial assistance for: -Transportation, Utilities, Food, Child Care, Housing Costs Type and amount of assistance is determined on a case by case basis by the Foundation’s Financial Aid Review Committee. An application is required. This Organization targets young women with breast cancer, but is available to women of all ages who are in active treatment for breast cancer. Also provides health educational presentations by healthcare professionals to focus on breast cancer awareness, prevention, screening and early detection. Monthly support groups – call for meeting information. https://www.jdbreastcancer.org/
| Karen P. Nakon Foundation | 35765 Chester Road Avon, Ohio 44011 | 440-213-9882 | Their mission is to provide financial aid to families in Northern Ohio impacted by a breast cancer diagnosis. Website: www.nakonfoundation.org
| United Way | 1875 North Ridge Road E # H Lorain, OH 44055 | 4402776530 | Everyone deserves opportunities to have a good life: a quality education that leads to a stable job, enough income to support a family through retirement, and good health. That's why the United Way of Greater Lorain County's work is focused on the building blocks for a good life: Education – Helping Children and Youth Achieve Their Potential, Income – Promoting Financial Stability and Independence, Health – Improving People's Health United Way's goal is to create long-lasting changes by addressing the underlying causes of these problems. Living United means being a part of the change. It takes everyone in the community working together to create a brighter future. Give. Advocate. Volunteer. LIVE UNITED. Website: www.uwloraincounty.org/
Food Sources | Power 4 Pink, Inc. | P.O. Box 1034 Amherst, OH 44001 |  | Meijer cards provided to help with grocery needs. (Current Power 4 Pink patients only) www.power4pink.com
| FreshTrak |  |  | Website is www.Freshtrak.com. Lists local food banks, pantries and food sources for next 6 weeks. Lookup is by zipcode.
| Neighborhood Alliance | 1536 E 30th St Lorain, OH 44055 | 440.233.8768 option #2 | Provide home delivered meals for weekdays to senior residents.
| Second Harvest Food Bank | 5510 Baumhart Rd Lorain, OH 44053 | 440-960-2265 | To receive food at a Second Harvest distribution or a partner charity food pantry, you must self-declare that you are income eligible Website: https://www.secondharvestfoodbank.org
Mammograms/ Breast Ultrasounds | Mercy Regional Medical Center | 3700 Kolbe Road Lorain Ohio 44052 | (440) 960-3624 | Offers events quarterly with free mammograms, clinical breast exams, and breast self examination instruction.
| University Hospital | Avon, Elyria, and Westlake Locations | 8663081787 | University Hospitals serves the community through a partnership with the Breast and Cervical Cancer Project. Through income-based eligibility, women have access to free mammograms and breast ultrasounds.
Personal Hygiene Products | Salvation Army | 370 W. Lincoln Street Oberlin, Oh 44074 | 4403289060 | Offers personal hygiene products free of charge to low income Lorain County residents.
Prostetics/Bra's | Ever You | P.O. Box 62244 Cincinnati, OH 45262 | 800-850-9445 | We know how cancer steals so many things that make us feel like ourselves. At EverYou™, formerly “tlc” Tender Loving Care®, you’ll find the best quality wigs, headwear and mastectomy products to help you keep looking and feeling like yourself. Website: https://everyou.com
| Elegant Essentials | 5164 Normandy Park Dr #300 Medina, OH 44256 | (330) 723-8880 | Whether or not you seek us out as a result of a mastectomy, lumpectomy, reconstruction, asymmetry or simply because you’re uncomfortable with your everyday bras, Elegant Essentials provides solutions to all of these issues. From breast prostheses, fashionable bras, specialty clothing with built-in bras to hats and headwear, compression garments for lymphedema, swimwear and gifts and jewelry, you will find an extensive selection of items just for you. Website: www.elegantessentialsonline.com
Support Groups | Mercy Cancer Center | 41201 Schaden Road Elyria OH 44035 | 4403240400 | The Center for Body, Mind, and Spirit has programs for those touched by cancer. Website: www.mercyonline.org/cancer.aspx
| After Breast Cancer Diagnosis (ABCD) Breast Cancer Support Group |  | 8009774121 | ABCD offers free emotional support services to empower anyone impacted by a breast cancer diagnosis Website: www.abcdbreastcancersupport.org
| Cancer Care |  | 8008134673 | Provides support for those touched by cancer. Website: www.cancercare.org
| The Gathering Place | 25425 Center Ridge Rd Westlake, Oh 44145 | 216-455-1507 | Free support programs and services. Many are virtual groups. Website: www.touchedbycancer.org
Transportation | Power 4 Pink, Inc. | P.O. Box 1034 Amherst, OH 44001 |  | Gas Cards provided to get to appointments and treatments. (Current Power 4 Pink patients only) www.power4pink.com
| Lorain County Transit | 226 Middle Ave Elyria, OH 44035 | 4403295525 | Organization offers ground transportation services for medical appointments for patients and family members. Dial-a-ride services are open to Lorain County residents; offering discounted fares to seniors and disabled individuals. Scheduling should be done two weeks in advance. May be able to accommodate later notices if appointment is during the day. Website: www.loraincounty.us
Wigs / Salons | Power 4 Pink, Inc. | P.O. Box 1034 Amherst, Oh 44001 | 4406543487 | Power 4 Pink will present their survivors with a cut and style with A.David Anthony salon upon completion of their treatment. (Current Power 4 Pink patients only) www.power4pink.com
| A Beau Monde Salon | 1895 Cooper Foster Park Rd Amherst, OH 44001 | (440) 935-7136 | Houses a wig bank for The American Cancer Society that provides a free wig to cancer patients living in Erie and Lorain Counties. Please call to arrange an appointment. This salon will also cut and style the wig free of charge for the cancer patient.
Various National Information Sites | Amercian Cancer Society |  | 8002272345 | Provides extensive data and facts about breast cancer. Website: www.cancer.org
| American Breast Cancer Foundation |  |  | We aim to aid in the early detection, treatment, and survival of breast cancer in patients. www.abcf.org
| American Cancer Society |  |  | Provides extensive data and facts about breast cancer. Website: https://www.cancer.org/cancer/types/breast-cancer
| Breast Cancer Research Foundation |  |  | Primarily dedicated to funding breast cancer research. www.bcrf.org
| Breast Cancer.Org |  |  | Considered a top website for comprehensive breast cancer information and a strong peer support community. Website: www.breastcancer.org
| National Breast Cancer Foundation |  |  | Focuses on educational resources and providing access to screening mammograms for underserved individuals. www.nationalbreastcancer.org
| National Cancer Institute |  | (800) 4-CANCER | Includes information regarding national nonprofit organizations that provide financial and emotional support, advocacy, and information to cancer patients and their families. Website: http://www.cancer.gov/cancertopics/types/breast
| Susan G. Komen |  |  | Offers a breast care helpline and support for those affected by breast cancer. www.komen.org
Suggested Books | Dr. Susan Love's Breast Book
Cancer Has it's Privledges -Christine Clifford
Why I Wore Lipstick to My Mastectomy by Geralyn Lucas
Rev 3/25